## Sheet1
SPRINT 6 PLANNING DOCUMENT | PURPLE TEAM |  |  | TEAM TASK CHECKLIST
ITEM | Assigned to | Time Est | Time Actual | TYLER | CHANG | TJ | SAI | SHRAVYA
PLANNING (SCRUM 1) 4/16
New Sprint Task sheet | Tyler | 10 min | 5 min
Lessons learned from sprint 5 | TJ | 10 min | 10 min
Update Trello | ALL | 10 min | 10 min
FINSIHING UP (SCRUM 2) 4/18
5 use cases/description | ALL | 30 min | 30 min
Link to other teams using queries | TJ
SQL for all queries | Tyler
Implement using SSRS | Chang
Star schemas (2 local, 4 master) | ALL
Implement star schemas in SSAS | Shravya
Implement using Pivot | ALL
QlikView ??? | ALL
COMPILATION (SCRUM 3) 4/23
Compile the following: | ALL
Sprint planning documents
Video Scripts
Lessons Learned
Video links
Tasks/task analysis
All scrum minutes
Double check Final matrix | ALL
VIDEO (SCRUM 4) 4/25
Create Video | ALL
Compile deliverables and submit | ALL